## export
Department | Request Type | RFQ Description | Tender Type | Approval Authority | Estimation Amount ($) | Contract Holder | SCM Analyst | Requisition Number | RFQ Number | Created PO | Current Tendering Status | Stage Progress Status | Overall Progress Status | Tender Progress Remarks | Tender Plan Line Number | Revision Number | Status | BPA Number | PO Description | Final Award Amount | Current Contractor | Contract Description | Contract End Date | Pre Qualification | Mobilization Months | Shared Scope/Project | Tender Requirements | Criticality | ICV | Oman Work Force | User Remarks | SCM Remarks | VTC Number | Request Raised Date | User Approval Date | VTC Assigned Date | Buyer Approval Date | Initiate/Discuss | Req's Approval | Tender Strategy Issuance | Tender Strategy Approval | Publish Days | Bid Close Days | Open Technical Submissions | Complete Tech Evaluation | Approval Technical Evaluation | Open Comm Submissions | Complete Comm Evaluation Days | Award Approval | LOA Issuance | SPO/BPA IssuanceDays | Initiate/Discuss | Req's Approval | Tender Strategy Issuance | Tender Strategy Approval | Publish Date | Bid Close Date | Open Technical Submissions | Complete Tech Evaluation | Approval Technical Evaluation | Open Comm Submissions | Complete Comm Evaluation Days | Award Approval | LOA Issuance | SPO/BPA IssuanceDays | Initiate/ Discuss | Req's Approval | Tender Strategy Issuance | Tender Strategy Approval | Publish Date | Bid Close Date | Open Technical Submissions | Complete Tech Evaluation | Approval Technical Evaluation | Open Comm Submissions | Complete Comm Evaluation Days | Award Approval | LOA Issuance | SPO/ BPA IssuanceDays
IMT | New | Manage Engine AD Audit Plus, ADManager Plus | Competitive Bidding | ITC | 144000 | Lujaina Al Lamki | Adil Ali Abdullah Al Siyabi | 1049361 | DALEEL-21-185-2 |  | LOA Issuance | Off Track | Award Off Track |  | TP_518 | 2 | Accepted | [7 empty] | 0 | [12 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-01-09 | 2021-04-19 | 2021-05-03 | 2021-05-24 | 2021-05-31 | 2021-06-21 | 2021-06-24 | 2021-08-09 | 2021-08-23 | 2021-08-26 | 2021-09-16 | 2021-09-30 | 2021-10-07 | 2021-10-28 |  | 2021-04-19 | 2021-07-04 | 2021-07-11 | 2021-07-11 | 2021-07-29 | 2021-08-01 | 2021-08-25 | 2021-08-31 | 2021-09-01 | 2021-09-26 | 2021-10-06
IMT | New | Cisco access switches ( business and automation) | Competitive Bidding | ITC | 312000 | Lujaina Al Lamki | Hasina Khalfan Said Al Shabibi | 1050454 | DALEEL-21-211 |  | Technical Approval | On Track | On Track |  | TP_367 | 2 | Accepted | [7 empty] | 0 | [12 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-12 | 2021-06-20 | 2021-07-04 | 2021-07-18 | 2021-07-25 | 2021-06-22 | 2021-08-18 | 2021-10-03 | 2021-10-17 | 2021-10-20 | 2021-11-10 | 2021-11-24 | 2021-12-08 | 2021-12-22 |  | 2021-06-20 | 2021-06-29 | 2021-07-12 | 2021-07-12 | 2021-08-19 | 2021-08-19 | 2021-10-11 | 2021-09-01 | 2021-09-02 | 2021-09-27 | 2021-10-07
IMT | New | Signature Manager Exchange Edition 2.0 | Competitive Bidding | ITC | 38937.3863 | Lujaina Al Lamki | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-3 |  | Commercial Evaluation | Award Off Track | Award On Track |  | TP_368 | 0 | Not Due | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-13 | 2021-06-21 | 2021-07-05 | 2021-07-19 | 2021-07-26 | 2021-06-23 | 2021-08-19 | 2021-10-04 | 2021-10-18 | 2021-10-21 | 2021-11-11 | 2021-11-25 | 2021-12-09 | 2021-12-23 |  | 2021-06-21 | 2021-06-30 | 2021-07-13 | 2021-07-13 | 2021-08-20 | 2021-08-20 | 2021-10-12 | 2021-09-02 | 2021-09-03 | 2021-09-28 | 2021-10-08
IMT | New | Acronis Backup Renewal for 3 years | Competitive Bidding | ITC | 42795.1936 | Lujaina Al Lamki | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-4 |  | Technical Evaluation | Award Off Track | Award On Track |  | TP_369 | 1 | Not Due | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-14 | 2021-06-22 | 2021-07-06 | 2021-07-20 | 2021-07-27 | 2021-06-24 | 2021-08-20 | 2021-10-05 | 2021-10-19 | 2021-10-22 | 2021-11-12 | 2021-11-26 | 2021-12-10 | 2021-12-24 |  | 2021-06-22 | 2021-07-01 | 2021-07-14 | 2021-07-14 | 2021-08-21 | 2021-08-21 | 2021-10-13 | 2021-09-03 | 2021-09-04 | 2021-09-29 | 2021-10-09
IMT | New | Riverbed support renewal for 3 years | Competitive Bidding | ITC | 34824.6298 | Mohammed Al Abri | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-5 |  | LOA Issuance | On Track | Award On Track |  | TP_370 | 0 | On Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-15 | 2021-06-23 | 2021-07-07 | 2021-07-21 | 2021-07-28 | 2021-06-25 | 2021-08-21 | 2021-10-06 | 2021-10-20 | 2021-10-23 | 2021-11-13 | 2021-11-27 | 2021-12-11 | 2021-12-25 |  | 2021-06-23 | 2021-07-02 | 2021-07-15 | 2021-07-15 | 2021-08-22 | 2021-08-22 | 2021-10-14 | 2021-09-04 | 2021-09-05 | 2021-09-30 | 2021-10-10
IMT | New | Renewal of Nintex Edition for 3 years | Competitive Bidding | ITC | 139906.4692 | Lujaina Al Lamki | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-6 |  | Technical Approval | Award On Track | Off Track |  | TP_371 | 2 | Revised | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-16 | 2021-06-24 | 2021-07-08 | 2021-07-22 | 2021-07-29 | 2021-06-26 | 2021-08-22 | 2021-10-07 | 2021-10-21 | 2021-10-24 | 2021-11-14 | 2021-11-28 | 2021-12-12 | 2021-12-26 |  | 2021-06-24 | 2021-07-03 | 2021-07-16 | 2021-07-16 | 2021-08-23 | 2021-08-23 | 2021-10-15 | 2021-09-05 | 2021-09-06 | 2021-10-01 | 2021-10-11
IMT | New | PROVISION OF FIDELIS CYBERSECURITY LICENSES AND MAINTENANCE RENEWAL | Competitive Bidding | ITC | 34619.3817 | Hamed Al Jabri | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-7 |  | Commercial Evaluation | Award On Track | Award Off Track |  | TP_372 | 1 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-17 | 2021-06-25 | 2021-07-09 | 2021-07-23 | 2021-07-30 | 2021-06-27 | 2021-08-23 | 2021-10-08 | 2021-10-22 | 2021-10-25 | 2021-11-15 | 2021-11-29 | 2021-12-13 | 2021-12-27 |  | 2021-06-25 | 2021-07-04 | 2021-07-17 | 2021-07-17 | 2021-08-24 | 2021-08-24 | 2021-10-16 | 2021-09-06 | 2021-09-07 | 2021-10-02 | 2021-10-12
IMT | New | Oracle Linux support contract for 3 years | Competitive Bidding | Below $50K | 72746.1678 | Azhar Al Barwani | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-8 |  | Technical Evaluation | Award On Track | Award Off Track |  | TP_373 | 2 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-18 | 2021-06-26 | 2021-07-10 | 2021-07-24 | 2021-07-31 | 2021-06-28 | 2021-08-24 | 2021-10-09 | 2021-10-23 | 2021-10-26 | 2021-11-16 | 2021-11-30 | 2021-12-14 | 2021-12-28 |  | 2021-06-26 | 2021-07-05 | 2021-07-18 | 2021-07-18 | 2021-08-25 | 2021-08-25 | 2021-10-17 | 2021-09-07 | 2021-09-08 | 2021-10-03 | 2021-10-13
IMT | New | Oracle VAT Implementation R12.2.6 | Competitive Bidding | ITC | 181930.3715 | Buthaina Saud Hilal Al Barwani | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-9 |  | LOA Issuance | Off Track | On Track |  | TP_374 | 2 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-19 | 2021-06-27 | 2021-07-11 | 2021-07-25 | 2021-08-01 | 2021-06-29 | 2021-08-25 | 2021-10-10 | 2021-10-24 | 2021-10-27 | 2021-11-17 | 2021-12-01 | 2021-12-15 | 2021-12-29 |  | 2021-06-27 | 2021-07-06 | 2021-07-19 | 2021-07-19 | 2021-08-26 | 2021-08-26 | 2021-10-18 | 2021-09-08 | 2021-09-09 | 2021-10-04 | 2021-10-14
IMT | New | Provsion of Datacenter Maintenance Services | Competitive Bidding | ITC | 209281.21 | Buthaina Saud Hilal Al Barwani | Buthaina Saud Hilal Al Barwani | 1050454 | DALEEL-21-185-10 |  | Technical Approval | Off Track | Award On Track |  | TP_375 | 2 | On Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-20 | 2021-06-28 | 2021-07-12 | 2021-07-26 | 2021-08-02 | 2021-06-30 | 2021-08-26 | 2021-10-11 | 2021-10-25 | 2021-10-28 | 2021-11-18 | 2021-12-02 | 2021-12-16 | 2021-12-30 |  | 2021-06-28 | 2021-07-07 | 2021-07-20 | 2021-07-20 | 2021-08-27 | 2021-08-27 | 2021-10-19 | 2021-09-09 | 2021-09-10 | 2021-10-05 | 2021-10-15
IMT | New | Purchase and Maintenance for Subsurface Well Model (Petex) | Competitive Bidding | Below $50K | 423356.45 | Buthaina Saud Hilal Al Barwani | Abdullah Al Mawaali | 1050454 | DALEEL-21-185-11 |  | Commercial Evaluation | Off Track | Award On Track |  | TP_376 | 2 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-21 | 2021-06-29 | 2021-07-13 | 2021-07-27 | 2021-08-03 | 2021-07-01 | 2021-08-27 | 2021-10-12 | 2021-10-26 | 2021-10-29 | 2021-11-19 | 2021-12-03 | 2021-12-17 | 2021-12-31 |  | 2021-06-29 | 2021-07-08 | 2021-07-21 | 2021-07-21 | 2021-08-28 | 2021-08-28 | 2021-10-20 | 2021-09-10 | 2021-09-11 | 2021-10-06 | 2021-10-16
IMT | New | Implementing of Qlik Business Intelligent | Competitive Bidding | Below $50K | 109457.0018 | Ahmed Hamood Hamed Al Rashdi | Lujaina Al Lamki | 1050454 | DALEEL-21-185-12 |  | Technical Evaluation | On Track | Off Track |  | TP_377 | 1 | Not Due | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-22 | 2021-06-30 | 2021-07-14 | 2021-07-28 | 2021-08-04 | 2021-07-02 | 2021-08-28 | 2021-10-13 | 2021-10-27 | 2021-10-30 | 2021-11-20 | 2021-12-04 | 2021-12-18 | 2022-01-01 |  | 2021-06-30 | 2021-07-09 | 2021-07-22 | 2021-07-22 | 2021-08-29 | 2021-08-29 | 2021-10-21 | 2021-09-11 | 2021-09-12 | 2021-10-07 | 2021-10-17
IMT | New | Supply of IT Consumable Materials for Three (3) years | Competitive Bidding | ITC | 1073244 | Buthaina Saud Hilal Al Barwani | Hamed Al Jabri | 1050454 | DALEEL-21-185-13 |  | LOA Issuance | Award Off Track | Off Track |  | TP_378 | 1 | Not Due | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-23 | 2021-07-01 | 2021-07-15 | 2021-07-29 | 2021-08-05 | 2021-07-03 | 2021-08-29 | 2021-10-14 | 2021-10-28 | 2021-10-31 | 2021-11-21 | 2021-12-05 | 2021-12-19 | 2022-01-02 |  | 2021-07-01 | 2021-07-10 | 2021-07-23 | 2021-07-23 | 2021-08-30 | 2021-08-30 | 2021-10-22 | 2021-09-12 | 2021-09-13 | 2021-10-08 | 2021-10-18
IMT | New | Comprehensive process of reviewing, implementing & securing Oracle EBS for 3 yrs | Competitive Bidding | ITC | 288212.5227 | Lujaina Al Lamki | Adil Al Siyabi | 1050454 | DALEEL-21-185-14 |  | Technical Approval | Award Off Track | Award On Track |  | TP_379 | 0 | On Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-24 | 2021-07-02 | 2021-07-16 | 2021-07-30 | 2021-08-06 | 2021-07-04 | 2021-08-30 | 2021-10-15 | 2021-10-29 | 2021-11-01 | 2021-11-22 | 2021-12-06 | 2021-12-20 | 2022-01-03 |  | 2021-07-02 | 2021-07-11 | 2021-07-24 | 2021-07-24 | 2021-08-31 | 2021-08-31 | 2021-10-23 | 2021-09-13 | 2021-09-14 | 2021-10-09 | 2021-10-19
IMT | New | Support contract for Datacenter Active components Renewal(Servers & Storage) | Competitive Bidding | ITC | 71506.8849 | Buthaina Saud Hilal Al Barwani | Lujaina Al Lamki | 1050454 | DALEEL-21-185-15 |  | Commercial Evaluation | On Track | Off Track |  | TP_380 | 1 | Off Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-25 | 2021-07-03 | 2021-07-17 | 2021-07-31 | 2021-08-07 | 2021-07-05 | 2021-08-31 | 2021-10-16 | 2021-10-30 | 2021-11-02 | 2021-11-23 | 2021-12-07 | 2021-12-21 | 2022-01-04 |  | 2021-07-03 | 2021-07-12 | 2021-07-25 | 2021-07-25 | 2021-09-01 | 2021-09-01 | 2021-10-24 | 2021-09-14 | 2021-09-15 | 2021-10-10 | 2021-10-20
IMT | New | Supply of Tape Library for HQ & Field Data Center. | Competitive Bidding | ITC | 58100 | Buthaina Saud Hilal Al Barwani |  | 1050454 | DALEEL-21-185-16 |  | Technical Evaluation | Award On Track | Award Off Track |  | TP_381 | 2 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-26 | 2021-07-04 | 2021-07-18 | 2021-08-01 | 2021-08-08 | 2021-07-06 | 2021-09-01 | 2021-10-17 | 2021-10-31 | 2021-11-03 | 2021-11-24 | 2021-12-08 | 2021-12-22 | 2022-01-05 |  | 2021-07-04 | 2021-07-13 | 2021-07-26 | 2021-07-26 | 2021-09-02 | 2021-09-02 | 2021-10-25 | 2021-09-15 | 2021-09-16 | 2021-10-11 | 2021-10-21
IMT | New | Implementation of Distributed Denial of Service(DDoS) Protection Solution 1 year | Competitive Bidding | ITC | 33528.1891 | Buthaina Saud Hilal Al Barwani | Abdullah Al Mawaali | 1050454 | DALEEL-21-185-17 |  | LOA Issuance | Award On Track | Award On Track |  | TP_382 | 2 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-27 | 2021-07-05 | 2021-07-19 | 2021-08-02 | 2021-08-09 | 2021-07-07 | 2021-09-02 | 2021-10-18 | 2021-11-01 | 2021-11-04 | 2021-11-25 | 2021-12-09 | 2021-12-23 | 2022-01-06 |  | 2021-07-05 | 2021-07-14 | 2021-07-27 | 2021-07-27 | 2021-09-03 | 2021-09-03 | 2021-10-26 | 2021-09-16 | 2021-09-17 | 2021-10-12 | 2021-10-22
IMT | New | Development, Hosting of Daleel External Website & 3 Years Annual Maintenance Co | Competitive Bidding | ITC | 166487.3993 | Lujaina Al Lamki | Adil Al Siyabi | 1050454 | DALEEL-21-185-18 |  | Technical Approval | Award On Track | On Track |  | TP_383 | 0 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-28 | 2021-07-06 | 2021-07-20 | 2021-08-03 | 2021-08-10 | 2021-07-08 | 2021-09-03 | 2021-10-19 | 2021-11-02 | 2021-11-05 | 2021-11-26 | 2021-12-10 | 2021-12-24 | 2022-01-07 |  | 2021-07-06 | 2021-07-15 | 2021-07-28 | 2021-07-28 | 2021-09-04 | 2021-09-04 | 2021-10-27 | 2021-09-17 | 2021-09-18 | 2021-10-13 | 2021-10-23
IMT | New | Provision of Items & Services Cataloging Solution | Competitive Bidding | Below $50K | 85022.0837 | Lujaina Al Lamki | Mohammed Al Abri | 1050454 | DALEEL-21-185-19 |  | Commercial Evaluation | Award On Track | On Track |  | TP_384 | 1 | On Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-29 | 2021-07-07 | 2021-07-21 | 2021-08-04 | 2021-08-11 | 2021-07-09 | 2021-09-04 | 2021-10-20 | 2021-11-03 | 2021-11-06 | 2021-11-27 | 2021-12-11 | 2021-12-25 | 2022-01-08 |  | 2021-07-07 | 2021-07-16 | 2021-07-29 | 2021-07-29 | 2021-09-05 | 2021-09-05 | 2021-10-28 | 2021-09-18 | 2021-09-19 | 2021-10-14 | 2021-10-24
IMT | New | Provision of Supply of Data Loss Prevention, Device Control Solution and Protect | Competitive Bidding | Below $50K | 17661.7303 | Mohammed Al Abri | Lujaina Al Lamki | 1050454 | DALEEL-21-185-20 |  | Technical Evaluation | Off Track | Award On Track |  | TP_385 | 0 | Off Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-30 | 2021-07-08 | 2021-07-22 | 2021-08-05 | 2021-08-12 | 2021-07-10 | 2021-09-05 | 2021-10-21 | 2021-11-04 | 2021-11-07 | 2021-11-28 | 2021-12-12 | 2021-12-26 | 2022-01-09 |  | 2021-07-08 | 2021-07-17 | 2021-07-30 | 2021-07-30 | 2021-09-06 | 2021-09-06 | 2021-10-29 | 2021-09-19 | 2021-09-20 | 2021-10-15 | 2021-10-25
IMT | New | Support for ICV Monitoring and Reporting system. | Competitive Bidding | ITC | 19870.0961 | Mohammed Al Abri | Lujaina Al Lamki | 1050454 | DALEEL-21-185-21 |  | LOA Issuance | Off Track | Award On Track |  | TP_386 | 2 | Off Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-03-31 | 2021-07-09 | 2021-07-23 | 2021-08-06 | 2021-08-13 | 2021-07-11 | 2021-09-06 | 2021-10-22 | 2021-11-05 | 2021-11-08 | 2021-11-29 | 2021-12-13 | 2021-12-27 | 2022-01-10 |  | 2021-07-09 | 2021-07-18 | 2021-07-31 | 2021-07-31 | 2021-09-07 | 2021-09-07 | 2021-10-30 | 2021-09-20 | 2021-09-21 | 2021-10-16 | 2021-10-26
IMT | New | License Renewal of Kaspersky Endpoint Security for Business Advanced | Competitive Bidding | ITC | 201152.2473 | Adil Al Siyabi | Hamed Al Jabri | 1050454 | DALEEL-21-185-22 |  | Technical Approval | Off Track | Off Track |  | TP_387 | 2 | Off Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-01 | 2021-07-10 | 2021-07-24 | 2021-08-07 | 2021-08-14 | 2021-07-12 | 2021-09-07 | 2021-10-23 | 2021-11-06 | 2021-11-09 | 2021-11-30 | 2021-12-14 | 2021-12-28 | 2022-01-11 |  | 2021-07-10 | 2021-07-19 | 2021-08-01 | 2021-08-01 | 2021-09-08 | 2021-09-08 | 2021-10-31 | 2021-09-21 | 2021-09-22 | 2021-10-17 | 2021-10-27
IMT | New | Application of ArcGIS System. | Competitive Bidding | ITC | 730834.5025 | Adil Al Siyabi | Malik Al Abri | 1050454 | DALEEL-21-185-23 |  | Commercial Evaluation | Award On Track | Off Track |  | TP_388 | 2 | On Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-02 | 2021-07-11 | 2021-07-25 | 2021-08-08 | 2021-08-15 | 2021-07-13 | 2021-09-08 | 2021-10-24 | 2021-11-07 | 2021-11-10 | 2021-12-01 | 2021-12-15 | 2021-12-29 | 2022-01-12 |  | 2021-07-11 | 2021-07-20 | 2021-08-02 | 2021-08-02 | 2021-09-09 | 2021-09-09 | 2021-11-01 | 2021-09-22 | 2021-09-23 | 2021-10-18 | 2021-10-28
IMT | New | Provision of Disaster Recovery Solution | Competitive Bidding | ITC | 171810 | Lujaina Al Lamki | Azhar Al Barwani | 1050454 | DALEEL-21-185-24 |  | Technical Evaluation | Off Track | Award Off Track |  | TP_389 | 2 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-03 | 2021-07-12 | 2021-07-26 | 2021-08-09 | 2021-08-16 | 2021-07-14 | 2021-09-09 | 2021-10-25 | 2021-11-08 | 2021-11-11 | 2021-12-02 | 2021-12-16 | 2021-12-30 | 2022-01-13 |  | 2021-07-12 | 2021-07-21 | 2021-08-03 | 2021-08-03 | 2021-09-10 | 2021-09-10 | 2021-11-02 | 2021-09-23 | 2021-09-24 | 2021-10-19 | 2021-10-29
IMT | New | Implementation and Support of HSE Education Center System | Competitive Bidding | ITC | 217781.2419 | Hamed Al Jabri | Aida Al Barwani | 1050454 | DALEEL-21-185-25 |  | LOA Issuance | Off Track | Award Off Track |  | TP_390 | 2 | Rejected | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-04 | 2021-07-13 | 2021-07-27 | 2021-08-10 | 2021-08-17 | 2021-07-15 | 2021-09-10 | 2021-10-26 | 2021-11-09 | 2021-11-12 | 2021-12-03 | 2021-12-17 | 2021-12-31 | 2022-01-14 |  | 2021-07-13 | 2021-07-22 | 2021-08-04 | 2021-08-04 | 2021-09-11 | 2021-09-11 | 2021-11-03 | 2021-09-24 | 2021-09-25 | 2021-10-20 | 2021-10-30
IMT | New | VMware Licenses Renewal & Consolidation | Competitive Bidding | ITC | 468994.544 | Buthaina Saud Hilal Al Barwani | Lujaina Al Lamki | 1050454 | DALEEL-21-185-26 |  | Technical Approval | Award On Track | On Track |  | TP_391 | 1 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-05 | 2021-07-14 | 2021-07-28 | 2021-08-11 | 2021-08-18 | 2021-07-16 | 2021-09-11 | 2021-10-27 | 2021-11-10 | 2021-11-13 | 2021-12-04 | 2021-12-18 | 2022-01-01 | 2022-01-15 |  | 2021-07-14 | 2021-07-23 | 2021-08-05 | 2021-08-05 | 2021-09-12 | 2021-09-12 | 2021-11-04 | 2021-09-25 | 2021-09-26 | 2021-10-21 | 2021-10-31
IMT | New | Enterprise Unified Storage Systems Design | Competitive Bidding | ITC | 259288.1268 | Adil Al Siyabi | Hamed Al Jabri | 1050454 | DALEEL-21-185-27 |  | Commercial Evaluation | Award Off Track | Award On Track |  | TP_392 | 1 | Off Track | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-06 | 2021-07-15 | 2021-07-29 | 2021-08-12 | 2021-08-19 | 2021-07-17 | 2021-09-12 | 2021-10-28 | 2021-11-11 | 2021-11-14 | 2021-12-05 | 2021-12-19 | 2022-01-02 | 2022-01-16 |  | 2021-07-15 | 2021-07-24 | 2021-08-06 | 2021-08-06 | 2021-09-13 | 2021-09-13 | 2021-11-05 | 2021-09-26 | 2021-09-27 | 2021-10-22 | 2021-11-01
IMT | New | Enterprise Backup Storage Systems. | Competitive Bidding | ITC | 17147.311 | Buthaina Saud Hilal Al Barwani | Adil Al Siyabi | 1050454 | DALEEL-21-185-28 |  | Technical Evaluation | Award Off Track | Award Off Track |  | TP_393 | 1 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-07 | 2021-07-16 | 2021-07-30 | 2021-08-13 | 2021-08-20 | 2021-07-18 | 2021-09-13 | 2021-10-29 | 2021-11-12 | 2021-11-15 | 2021-12-06 | 2021-12-20 | 2022-01-03 | 2022-01-17 |  | 2021-07-16 | 2021-07-25 | 2021-08-07 | 2021-08-07 | 2021-09-14 | 2021-09-14 | 2021-11-06 | 2021-09-27 | 2021-09-28 | 2021-10-23 | 2021-11-02
IMT | New | Blade SAN Switch | Competitive Bidding | ITC | 43120.291 | Lujaina Al Lamki | Adil Al Siyabi | 1050454 | DALEEL-21-185-29 |  | LOA Issuance | Award On Track | Award On Track |  | TP_394 | 0 | Approved | [20 empty] | 90 | 10 | 14 | 21 | 7 | 21 | 3 | 46 | 14 | 3 | 21 | 14 | 7 | 14 | 2021-04-08 | 2021-07-17 | 2021-07-31 | 2021-08-14 | 2021-08-21 | 2021-07-19 | 2021-09-14 | 2021-10-30 | 2021-11-13 | 2021-11-16 | 2021-12-07 | 2021-12-21 | 2022-01-04 | 2022-01-18 |  | 2021-07-17 | 2021-07-26 | 2021-08-08 | 2021-08-08 | 2021-09-15 | 2021-09-15 | 2021-11-07 | 2021-09-28 | 2021-09-29 | 2021-10-24 | 2021-11-03